## Quotation Summary
HyperTransfer — Phase 1 Client Application
Development Quotation · User-Side Application & All Provider Integrations
Prepared by: Heypervelocity · Client: HyperTransfer / Heypervelocity · https://h5.hypercypto.com
Quote No: HT-2026-001 · Date: 21 May 2026 · Valid Until: 21 Jun 2026 · Currency: USD
Item | Deliverable / Integration | Person-Days | Unit Price (USD/Day) | Amount (USD)
01 | Landing Page, Registration & Sign In | 18 | 450 | 8100
02 | KYC Identity Verification | 30 | 450 | 13500
03 | Dashboard & Account Management | 20 | 450 | 9000
04 | Core Crypto Deposit Flow | 75 | 450 | 33750
05 | Transaction History & Receipts | 15 | 450 | 6750
06 | Referral & Invitation System | 10 | 450 | 4500
07 | Notifications & Communications | 15 | 450 | 6750
08 | Support Centre | 9 | 450 | 4050
09 | Application Security & Two-Factor Authentication (2FA) | 25 | 450 | 11250
10 | Hex Safe, KYT Screening, Travel Rule & Prime Broker API | 83 | 450 | 37350
11 | Testing, QA & Project Management | 25 | 450 | 11250
Development Fee (excl. tax) |  | 325 | 450 | 146250
Annual System Maintenance Fee (10%) |  |  |  | 14625
Development fee: USD 146,250 (excl. tax) · USD 450/person-day × 325 person-days
Team: 4 developers + 1 product manager · 13-week delivery timeline · 5 people × 13 weeks × 5 days = 325 person-days
Tech stack: Vue 3 (frontend) + Python (backend) + PostgreSQL
Annual maintenance fee: USD 14,625/year (10% of development fee), commencing after production go-live acceptance
All amounts are exclusive of applicable taxes.

## Detailed Scope & Pricing
DETAILED SCOPE & PRICING — HYPERTRANSFER PHASE 1
Heypervelocity · https://h5.hypercypto.com · HT-2026-001 · 21 May 2026 · Rate: USD 450/person-day
Tech stack: Vue 3 (frontend) · Python (backend) · PostgreSQL
Item | Deliverable | Scope of Work | Days | Unit Price (USD/Day) | Amount (USD)
01 | Landing Page, Registration & Sign In |  | 18 | 450 | 8100
| Mobile-first H5 landing page (Vue 3); HyperTransfer branding; 256-bit SSL / KYC Compliant / Travel Rule / Secure Custody trust badges; Create Account & Sign In CTAs; Terms & Privacy Policy. Referral code (HC-XXXX) URL-parameter parsing; 'Referred by [Name] · HC-8842' attribution card on landing (as shown on live site). Account registration: Full Legal Name, Email, Mobile + SMS OTP verification; password strength indicator; Terms consent. Sign In: JWT session; Forgot Password via SMS/email; account lockout after N failed attempts. |  | 18 | 450 | 8100
02 | KYC Identity Verification |  | 30 | 450 | 13500
| KYC form: Nationality selector, Date of Birth, ID Document Type (Passport / HKID / National ID / Driver's Licence), Document Number. Document upload: front + back of ID + selfie-with-ID photo; file type/size validation; secure upload to encrypted object storage; upload progress & retry. KYC provider integration (Sumsub / Onfido / Jumio): document OCR, face-match liveness check; async webhook for status updates; result normalisation (Pending → Approved / Rejected). KYC status management: Not Started → Submitted → Under Review → Approved / Rejected; 24-hour SLA messaging; rejection reason display; re-submission flow; deposit locked until approved. |  | 30 | 450 | 13500
03 | Dashboard & Account Management |  | 20 | 450 | 9000
| Main Dashboard: personalised welcome ('Welcome, User'); Account Status pill (On Hold / Active / Suspended); KYC verification prompt & CTA; Deposit Overview (completed count, pending); Recent Activity feed (last 5 transactions); bottom nav tabs: History · Support · Profile (matching live site). Profile & security settings: edit personal info, change password, 2FA setup screen. Session management: active sessions list, revoke other sessions, auto-logout on inactivity, security event notifications (new login, password change). |  | 20 | 450 | 9000
04 | Core Crypto Deposit Flow |  | 75 | 450 | 33750
| Asset selection: USDT, USDC, BTC, ETH. Network selection: Ethereum (ERC-20), TRON (TRC-20), BSC (BEP-20), Polygon, Solana, and more — matching FAQ 'all major networks' on live site. Source wallet declaration: patron sending-wallet address input; per-network format validation; expected amount entry. Pre-deposit KYT screening result display: risk level, screening decision; Pass → continue; EDD / Fail → block with explanation. [Backend integration in Item 10.] FATF Travel Rule data collection form: originator name (pre-filled from KYC), originator wallet address, physical address / national ID, transaction amount & date; threshold-based trigger (configurable); beneficiary VASP system-configured (not shown to user). [Submission to Hex Safe in Item 10.] Hex Safe deposit address: single-use address per deposit; address display with one-tap copy; QR code for mobile wallet scanning; expiry countdown timer. Broker conversion quote display (for BTC/ETH → USDT/USDC): indicative exchange rate, fee, converted amount before user confirmation. [Broker API in Item 10.] On-chain monitoring: real-time animated status screen; per-network confirmation thresholds; estimated completion time. Post-arrival transaction KYT result: Funds Clear confirmation receipt; Funds Dirty notification & hold state. Deposit error handling: address expired (regeneration offer), partial amount, wrong network advisory, abandoned-deposit timeout. |  | 75 | 450 | 33750
05 | Transaction History & Receipts |  | 15 | 450 | 6750
| Transaction history list (/history page, matching live site): paginated list; filter tabs All · Completed · Pending; row data: date, asset, amount, network, status. Transaction detail view: status timeline stepper (Initiated → Screened → Address Issued → Funds Detected → Confirmed); txHash linked to block explorer; conversion details where applicable; downloadable PDF receipt. Search & export: date range filter, asset/network filter, CSV export. |  | 15 | 450 | 6750
06 | Referral & Invitation System |  | 10 | 450 | 4500
| Corresponding pages: Landing page HC-XXXX 'Referred by' attribution card (live at h5.hypercypto.com) + Profile page (user's own referral code & sharing). Unique referral code per account (HC-XXXX format); referral link with URL parameter; share CTAs (copy link, WhatsApp, Telegram, QR code). Attribution tracking: URL-param capture + cookie persistence; referral chain recording; anti-gaming rules (same device/IP; one credit per unique verified account). Referral dashboard in Profile: referred users list, aggregate stats (total referred / pending / confirmed). |  | 10 | 450 | 4500
07 | Notifications & Communications |  | 15 | 450 | 6750
| SMS: OTP delivery; deposit status updates (address issued, funds detected, confirmed); KYC status (under review / approved / rejected); security events. Twilio / AWS SNS adapter with retry. Email: registration welcome; KYC submission confirmation; KYC approved/rejected; deposit confirmed with receipt; security alerts. HTML email templates, HyperTransfer branding. In-app & PWA Push: notification bell with unread badge; notification list (read/unread); Web Push API / service-worker setup; notification preference settings. |  | 15 | 450 | 6750
08 | Support Centre |  | 9 | 450 | 4050
| FAQ (/support page, live on site): structured Q&A matching live content (deposit timing 5–30 min, KYC 24hr, supported networks, data security, verification transfer failure); expandable accordion; CMS-ready for content updates without code deploy. Contact form & ticket: Subject + Message form; auto-reply acknowledgement; ticket reference number; message history for user. Call / Callback: click-to-call (tel: protocol); callback scheduling form with preferred date/time. |  | 9 | 450 | 4050
09 | Application Security & Two-Factor Authentication (2FA) |  | 25 | 450 | 11250
| Authentication & session security: JWT access token + refresh token (HttpOnly cookie); CSRF protection; rate limiting on auth endpoints; IP-based throttling; audit log for all auth events. Two-factor authentication (2FA): TOTP (Google Authenticator / Authy) with QR setup; SMS OTP backup; 2FA enforcement on high-value deposit actions; recovery codes; disable flow with re-auth. Application security hardening: input validation & XSS prevention; SQL injection prevention; dependency security audit (Snyk); API key vault management (no secrets in code); Content Security Policy (CSP) headers; secure file upload validation; 256-bit TLS/SSL; OWASP Top 10 compliance review. |  | 25 | 450 | 11250
10 | Hex Safe, KYT Screening, Travel Rule & Prime Broker API |  | 83 | 450 | 37350
| ─ Hex Safe Custody API (core deposit flow): · POST /vaults/{vaultId}/address — single-use deposit address per transaction · GET /deposit/{txHash} and GET /transactions/{traceId} — on-chain monitoring & status polling · POST /transactions/{chain} — sweep funds from deposit collection wallet to WTA treasury vault · POST /deposit/submit_travel_rule_details — FATF Travel Rule data submission to Hex Safe · Webhook receiver with Hex Safe request-signature verification; x-request-id idempotency header ─ FATF Travel Rule Backend: · Originator / beneficiary data model; threshold trigger logic (configurable per jurisdiction) · Submission to Hex Safe Travel Rule endpoint; status tracking (pending / submitted / rejected) · Data retained for regulatory audit and VASP compliance reporting ─ KYT Wallet Screening (pre-deposit + post-arrival — two independent layers): · Pluggable adapter: Chainalysis / TRM Labs / Elliptic (client selects vendor) · Pre-deposit: risk score, sanctions list check, tainted exposure %, mixer/darknet proximity, hop count; Pass / EDD / Fail gate blocks address issuance · Post-arrival: second independent KYT call on incoming txHash after funds detected via Hex Safe webhook; Funds Clear → settlement proceeds; Funds Dirty → hold + compliance case auto-created · All screening results and compliance decisions persisted for audit trail ─ Prime Broker / Conversion API: · Broker adapter for non-stable-coin deposits (BTC / ETH → USDT / USDC target asset) · Quote API: indicative exchange rate, fee, converted amount, quote expiry · Order execution: conversion after user confirmation · Stable-coin-to-stable-coin zero-commission swap path (e.g. USDT → USDC) · Conversion records stored with deposit for audit and reconciliation ─ Backend services & infrastructure: · User & Auth Service API (registration, login, OTP, JWT, roles, account status lifecycle) · Deposit state machine API (11-state lifecycle, validation, audit log write-through) · Referral, notification & communication service adapters (SMS / Email / Push) · PostgreSQL schema: users, kyc_records, deposits, transactions, conversions, referrals, notifications, compliance_cases, audit_logs, support_tickets · Cloud infrastructure: Docker, AWS/GCP, staging + production, GitHub Actions CI/CD, API gateway, uptime monitoring, error alerting (Sentry) |  | 83 | 450 | 37350
11 | Testing, QA & Project Management |  | 25 | 450 | 11250
| Integration & E2E testing: full deposit flow including KYT screening, Travel Rule, and broker conversion paths (Playwright / Cypress); KYC submission & webhook tests; referral attribution tests; API integration tests for all provider adapters (Hex Safe, KYT, KYC provider, broker); state machine unit tests. UAT support: 2 rounds with client; bug triage and fix sprints; regression testing; acceptance sign-off per deliverable. Performance & mobile testing: Lighthouse mobile audit (≥90 target); load test on deposit and KYT endpoints; iOS Safari + Android Chrome compatibility; 3G/4G network simulation. Documentation & PM: OpenAPI/Swagger API reference; Hex Safe + KYT + broker integration guides; Travel Rule data model docs; deployment runbook; operator guide; 13-week sprint coordination; weekly status reports; final handover package. |  | 25 | 450 | 11250
Development Fee (excl. tax) |  |  | 325 | 450 | 146250
Annual System Maintenance Fee (10% of development fee) |  |  |  |  | 14625
* Development fee: USD 146,250 (excl. tax). Unit rate: USD 450/person-day × 325 days.
* Annual maintenance: USD 14,625/year, commencing after production go-live acceptance.
* Team: 4 developers + 1 product manager. Delivery: 13 weeks.
* Tech stack: Vue 3 (frontend) + Python (backend) + PostgreSQL.
* Third-party API & subscription costs (Hex Safe, KYT, KYC, Broker, SMS, Email, Cloud) excluded — client-procured.
* Valid until 21 Jun 2026. All amounts exclusive of applicable taxes.

## Scope Notes
SCOPE NOTES — INCLUSIONS, EXCLUSIONS & ASSUMPTIONS
HyperTransfer — Phase 1 Client Application · Heypervelocity · HT-2026-001
INCLUSIONS — Covered in this quotation
✓ All frontend (Vue 3) and backend (Python) development
✓ Complete client-facing feature set as observed at h5.hypercypto.com (Phase 1)
✓ Hex Safe REST API — deposit address generation, on-chain monitoring, WTA sweep, withdrawal
✓ FATF Travel Rule — data collection, Hex Safe submission, regulatory data retention
✓ KYT wallet screening — pre-deposit AND post-arrival transaction screening (Chainalysis / TRM / Elliptic)
✓ Prime Broker / Conversion API — BTC/ETH → stablecoin and stable-to-stable swap path
✓ KYC identity verification adapter (Sumsub / Onfido / Jumio — client selects)
✓ Referral system (HC-XXXX code, attribution tracking, sharing, dashboard)
✓ Notifications: SMS (Twilio/SNS), Email (SendGrid/SES), In-app, PWA push
✓ Support centre: FAQ, contact form, callback request
✓ Application security hardening, 2FA (TOTP + SMS), OWASP Top 10 review
✓ CI/CD pipeline, Docker, staging + production cloud deployment
✓ Two rounds of UAT support and full integration test coverage
✓ Technical documentation, API reference, integration guides, deployment runbook
EXCLUSIONS — Not included in this quotation
✕ Hex Safe subscription / API fees — client-procured directly from Hex Trust
✕ KYT provider subscription (Chainalysis / TRM / Elliptic) — client-procured
✕ KYC provider subscription (Sumsub / Onfido / Jumio) — client-procured
✕ Prime Broker / conversion provider fees — client-procured
✕ SMS / Email service fees (Twilio, SendGrid, AWS) — client-procured
✕ Live chat / customer service platform (Crisp / Intercom) — client-procured and self-integrated
✕ Cloud infrastructure running costs (AWS / GCP) — client-procured
✕ Third-party penetration testing — recommended, procured separately
✕ Operator / admin back-office management panel — available as separate engagement
✕ Applicable taxes (quotation is exclusive of tax)
✕ Regulatory licensing or compliance legal advice
✕ Phase 2+ features (operator Pad App, treasury management, payout admin panel)
ASSUMPTIONS & CLIENT DEPENDENCIES
· Client provides Hex Safe API credentials and EC private key within 5 business days of contract signing
· Client selects and provides API keys for KYC provider, KYT provider, broker API, SMS and Email services within 5 days of kickoff
· Sandbox / testnet environments available for all third-party providers throughout development
· Client designates a product owner available ≥4 hours/week for sprint reviews and decisions
· UI/brand assets (logo, colours, fonts) provided within 3 days of kickoff, or h5.hypercypto.com is the approved design reference
· Cloud provider account (AWS or GCP) created and billing enabled by client before Week 10
· Change requests beyond agreed scope will be quoted separately at USD 450/person-day before work begins
· Delivery team: 4 developers + 1 product manager (5 people), 13-week delivery timeline
ACCEPTANCE / SIGN-OFF
Prepared by: Heypervelocity Signature: _________________________________ Date: ____________
Accepted by: Signature: _________________________________ Date: ____________