## Quotation Summary
QUOTATION
Virtual Asset Management Platform
Client: Wynn Macau · User-Side Development & Integration
Quote No: VA-2026-001 · Date: 19 May 2026 · Valid Until: 18 Jun 2026 · Currency: USD
PHASE SUMMARY
Phase | Description | Effort (hrs) | Amount (USD)
P1 | Phase 1 · Core Deposit Flow & Hex Safe Integration | 295 | 48200
P2 | Phase 2 · Compliance, KYC & Operations Dashboard | 175 | 28000
P3 | Phase 3 · Refund / Payout & Treasury Module | 125 | 20000
P4 | Phase 4 · Auth, Security & Okta Integration | 85 | 16200
P5 | Phase 5 · Testing, QA, DevOps & Documentation | 160 | 18200
TOTAL ENGAGEMENT |  | 840 | 130600
STANDARD RATE CARD
Role |  | Rate (USD/hr) | Scope
Tech Lead / Architect |  | 200 | Architecture, API design, security review
Senior Developer |  | 160 | Full-stack feature implementation
QA Engineer |  | 90 | Testing, UAT support
DevOps Engineer |  | 150 | CI/CD, infrastructure, deployment
Project Manager |  | 130 | Sprint coordination, reporting, stakeholder mgmt
All pricing is fixed-fee per phase. Hours shown are for scope transparency. Change requests outside agreed deliverables will be quoted at standard rates above.

## Detailed Scope & Pricing
DETAILED SCOPE & PRICING
Virtual Asset Management Platform · Wynn Macau
Quote: VA-2026-001 · Date: 19 May 2026 · Currency: USD
# | Deliverable | Description | Role | Hrs | Rate/hr | Amount
Phase 1 · Core Deposit Flow & Hex Safe Integration
1 | Project Architecture & Infrastructure Setup | Tech stack finalization, repo setup, CI/CD pipeline, environment config (dev/staging/prod), PostgreSQL schema design, API skeleton | Tech Lead | 25 | 200
2 | Employee Pad App — Main Deposit Flow | 9-step wizard: Login → Patron Lookup → Wallet Setup → KYT → Travel Rule → Address Issue → Monitoring → Compliance Clear → WTA. Role-based views for Host, Compliance, Treasury, Admin | Senior Dev | 65 | 160
3 | Hex Safe API Integration — Deposit Address Generation | POST /vaults/{vaultId}/address (single-use per deposit, BTC rotating address support); address metadata storage; expiry management; error handling & retry | Senior Dev | 35 | 160
4 | Hex Safe API Integration — Transaction Monitoring & Webhook | GET /deposit/{txHash}; GET /transactions/{traceId} polling; webhook endpoint with Hex Safe signature verification; deposit-request matching by addressId + txHash | Senior Dev | 35 | 160
5 | Hex Safe API Integration — WTA Vault Sweep | POST /transactions/{chain} for deposit-collection-to-WTA sweep; confirmation polling; sweep status reconciliation; GET /vaults/{id} balance refresh | Senior Dev | 20 | 160
6 | KYT Integration — Pre-Deposit Wallet Screening | Adapter interface for Chainalysis / TRM / Elliptic: risk score, sanctions hit, tainted exposure %, hop count, Pass/EDD/Fail gate. Result persistence; compliance gate before address issuance | Senior Dev | 35 | 160
7 | KYT Integration — Post-Arrival Transaction Screening | Second KYT call on real incoming txHash after funds detected; Funds Clear / Dirty determination; Dirty path: address voided, compliance case auto-created, deposit blocked | Senior Dev | 30 | 160
8 | Backend API — Deposit State Machine & Data Model | RESTful API for full deposit lifecycle (11 status states); Prisma ORM + PostgreSQL migrations; state transition guards; validation; audit log write-through on every action | Senior Dev | 50 | 160
Phase Subtotal — P1
Phase 2 · Compliance, KYC & Operations Dashboard
9 | KYC Module & Patron Management | Patron search (name / ID / jurisdiction); KYC status gate (verified / EDD / blocked / expired / missing); new patron onboarding form; Wynn CRM / gaming profile link; KYC routing rules | Senior Dev | 35 | 160
10 | FATF Travel Rule Integration | Originator/beneficiary data collection form; threshold logic (≥ configured amount or BTC/ETH); POST /deposit/submit_travel_rule_details to Hex Safe; Notabene / Sygna adapter interface; data retention | Senior Dev | 35 | 160
11 | Compliance Officer Dashboard & Case Management | EDD / Blocked / Funds Dirty case queue; case detail view; Approve / Reject / Request Documents / Close actions; reviewer assignment; priority escalation; full case history | Senior Dev | 40 | 160
12 | Operations Dashboard | Deposit queue with status/risk/date filters; deposit detail view; search and pagination; CSV export; exception highlights; role-based column visibility | Senior Dev | 30 | 160
13 | Audit Log & Compliance Reporting | Immutable audit trail (actor, action, entityType, timestamp, IP, deviceId); audit log query API; compliance reports for deposits, cases, Travel Rule submissions, transactions; PDF/CSV export | Senior Dev | 35 | 160
Phase Subtotal — P2
Phase 3 · Refund / Payout & Treasury Module
14 | Refund / Payout Pad Flow | Host/Finance initiates payout; patron selection; destination wallet pre-withdrawal KYT screening; Compliance Officer approval gate; submission to Hex Safe; real-time status tracking | Senior Dev | 40 | 160
15 | Hex Safe Withdrawal API Integration | POST /transactions/withdrawal with x-request-id idempotency; whitelist pre-check via GET /vaults/{id}/whitelist; multi-party approval polling; txHash broadcast confirmation | Senior Dev | 30 | 160
16 | Counterparty Book & Whitelist Management | GET/POST /counterparty; POST /counterparty/address/verify; operator UI for whitelist add/archive; whitelist validation on every outgoing transfer | Senior Dev | 20 | 160
17 | Treasury / WTA Dashboard | WTA vault balance from GET /vaults/{id}; pending settlement tracking; settled deposit history; cross-vault totals; Finance reconciliation view | Senior Dev | 35 | 160
Phase Subtotal — P3
Phase 4 · Auth, Security & Okta Integration
18 | Okta OIDC Integration | Authorization Code Flow with PKCE; Okta-hosted login redirect; ID/access token validation; Okta Groups → app role mapping; business session creation; logout and token revocation | Tech Lead | 25 | 200
19 | MFA & Step-Up Authentication | Okta Verify Push / Passkey (WebAuthn/FIDO2) as primary MFA; step-up auth trigger for high-risk actions (address issuance, EDD approval, payout submission); push fatigue mitigation | Tech Lead | 20 | 200
20 | Role-Based Access Control (RBAC) | Host / Compliance Officer / Treasury / Admin permission matrix; API-layer authorization middleware; UI conditional rendering; admin role management screen | Senior Dev | 20 | 160
21 | Security Hardening & Provider Key Management | Hex Safe API key + EC private key secure storage; KYT/Travel Rule API key rotation mechanism; rate limiting; webhook signature verification; OWASP Top 10 review checklist | Tech Lead | 20 | 200
Phase Subtotal — P4
Phase 5 · Testing, QA, DevOps & Documentation
22 | Integration & End-to-End Testing | Jest + React Testing Library for UI components; API integration tests for all provider adapters (Hex Safe, KYT, Travel Rule, Okta); deposit state machine unit tests; Zod schema tests; edge case coverage | QA | 50 | 90
23 | UAT Support & Bug Fixing | 2-round client UAT session support; bug triage and resolution sprints; regression testing; final acceptance sign-off documentation | QA | 30 | 90
24 | DevOps & Production Deployment | Docker containerization; staging + production environment provisioning; GitHub Actions CI/CD pipeline; database migration pipeline; uptime monitoring and error alerting setup | DevOps | 30 | 150
25 | Technical Documentation | API reference; provider adapter integration guide; Hex Safe authentication setup guide; deployment runbook; operator user guide; architecture decision records (ADRs) | PM | 20 | 130
26 | Project Management | Sprint planning and backlog management; weekly status reports to stakeholders; risk and dependency tracking; 8-week estimated delivery timeline coordination | PM | 30 | 130
Phase Subtotal — P5
TOTAL ENGAGEMENT COST | [5 empty] | 130600
* All amounts in USD. Prices are fixed-fee per phase.
* Third-party API subscription costs (Hex Safe, KYT provider, Okta) are excluded and client-procured.
* Payment schedule on 'Payment Milestones' sheet.
* Valid until 18 Jun 2026. Subject to re-quote if project start is delayed beyond this date.

## Payment Milestones
PAYMENT MILESTONES
Virtual Asset Management Platform · Wynn Macau
Total: USD 130,600 · 4 equal milestone payments
Milestone | Description | Deliverables / Acceptance Criteria | Target | Amount (USD)
M1 | Contract Signed & Kickoff | Project kickoff, architecture sign-off, dev environment ready | Week 0 | 32650
M2 | Phase 1 Complete — Core Deposit MVP | Working deposit flow with Hex Safe address generation, KYT, Travel Rule, on-chain monitoring | Week 3 | 32650
M3 | Phase 2 & 3 Complete — Compliance & Payout | Compliance dashboard, KYC module, audit trail, refund/payout flow, Treasury WTA view | Week 6 | 32650
M4 | Phase 4 & 5 Complete — Auth, Testing & Go-Live | Okta SSO, RBAC, security review, full QA, UAT sign-off, production deployment | Week 8 | 32650
TOTAL |  |  |  | 130600
PAYMENT TERMS
• Invoice issued upon achievement of each milestone, payable within 14 calendar days.
• All payments in USD by wire transfer or equivalent. Bank details provided upon contract signing.
• Late payments accrue interest at 1.5% per month after the due date.
• Milestone completion requires written acceptance from client's designated product owner.
• Should project be paused or cancelled, payment is due for all work completed to date.

## Scope Notes
SCOPE NOTES — INCLUSIONS, EXCLUSIONS & ASSUMPTIONS
Virtual Asset Management Platform · Wynn Macau
INCLUSIONS — What is covered in this quote
✓ All frontend (Next.js) and backend (Node.js/TypeScript) development
✓ Hex Safe REST API adapter (full endpoint mapping per documentation)
✓ KYT provider adapter (Chainalysis / TRM / Elliptic — client selects vendor)
✓ FATF Travel Rule adapter (Hex Safe native or Notabene / Sygna — client selects)
✓ Okta OIDC + MFA integration (client provides Okta tenant)
✓ PostgreSQL data model & migration scripts
✓ CI/CD pipeline and staging/production deployment
✓ Integration tests and UAT support (2 rounds)
✓ Technical documentation and operator guide
EXCLUSIONS — Not included in this quote
✗ Hex Safe, KYT provider, or Travel Rule provider subscription fees (client-procured)
✗ Okta tenant license and configuration (client-procured)
✗ Prime Broker / conversion flow (separate engagement)
✗ STR / SAR / HKFIO regulatory reporting integration
✗ Mobile approver app for Hex Safe multi-party approval
✗ Data migration from legacy systems
✗ Ongoing support and maintenance (available as separate retainer)
✗ Third-party penetration testing (recommended, client-procured separately)
ASSUMPTIONS & DEPENDENCIES
· Client provides Hex Safe API credentials, KYT provider API keys, and Okta tenant within 1 week of contract signing
· Sandbox / testnet environments available for all third-party providers
· Client designates a product owner available ≥4 hours/week for sprint reviews and decisions
· Design system / UI style guide provided by client within 1 week of kickoff (or approved use of existing demo style)
· Server infrastructure (cloud provider) selected and billing set up by client prior to Phase 5
· Change requests beyond agreed scope will be quoted separately at standard hourly rates
ACCEPTANCE
Prepared by: Development Partner Signature: _____________________________ Date: ____________
Accepted by: Wynn Macau Signature: _____________________________ Date: ____________